## Description
Building Info
For building administrators who want to minimise the costs of building management, our Building Info application will enable obtaining information about building parameters at the level of rooms, floors and entire buildings. The application will be available via GUI and also as a remote API, thanks to which it can be integrated with existing tools.
Data structure (to be placed in the README.md file) • A location is a building, level, or room • The building may consist of levels and those of rooms • Each location is characterized by: o id – unique identifier o name – optional name of the location • The room is additionally characterised by: o area = area in m^2 o cube = room volume in m^3 o heating = level of heating energy consumption (float) o light – total lighting power

## Product Backlog
Product Backlog item | Importance | Labour intensity | Business Value (BV) | Acceptance Criteria
As a developer of building management software, I can use the available functions remotely via REST to be able to integrate the tool with my other applications | 20 | 8 | 1 | o Input in JSON format corresponding to the building structure (lists, dictionaries) o Input transformed to an object model o Output in JSON format o REST API allows you to run any currently implemented function.
As a building manager, I can check the total area of a building, level or room in order to be able to do an area-based calculation | 15 | 4 | 1 | o Correctly calculated for a room o For a level, calculated as the sum of areas of rooms on the level o For a building, calculated as the sum of areas of levels
As a building manager, I can check the total volume of rooms in the building, on the level or take the cubature of the room in order to be able to calculate the volume of the rooms | 12 | 3 | 1 | o Correctly calculated for a room o For a level, calculated as the sum of volumes of rooms on the level o For a building, calculated as the sum of volumes of levels
As a building manager, I can calculate the lighting power per unit area for a building, level, room | 10 | 2 | 1 | o Correctly calculated for a room o For a level, calculated as the average power per m^2 per level o For a building, calculated as the average power on levels
As a building manager, I can calculate the heating energy consumption per unit of volume for a building, level, room | 10 | 3 | 1 | o Correctly calculated for a room o For a level, calculated as the average consumption per m^3 per level o For a building, calculated as the average consumption on levels
As a building manager, I can receive information about rooms in the building that exceed a certain level of heat consumption / m^3 given as a parameter to find places for improvement in the infrastructure. | 10 | 3 | 1.5 | o On the input, a limit value is specified in addition to the building structure o On the output, objects representing rooms exceeding the given standard
As a user, I can utilise the application via the user interface |  |  |  | To be negotiated later

## Sprint #1 Backlog
Sprint Goal: | Adding unit and mock tests
Product Backlog Item | Tasks | Labour intensity
As a developer of building management software, I can use the available functions remotely via REST to be able to integrate the tool with my other applications |  | 8
| Task #1 Learning about REST API | 2
| Task #2 Reading input JSON and basic parsing | 2
| Task #3 Transforming the output to the JSON format | 1
| Task #4 Connecting application to the REST API | 1
| Task #5 Validating and testing | 1
| Task #6 Debugging and cleaning code | 1
As a building manager, I can check the total area of a building, level or room in order to be able to do an area-based calculation |  | 4
| Task #1 Reading information about areas of the rooms | 1
| Task #2 Summing areas of all rooms for level | 1
| Task #3 Summing areas on all levels for building | 1
| Task #4 Debugging, testing and cleaning | 1
As a building manager, I can check the total volume of rooms in the building, on the level or take the cubature of the room in order to be able to calculate the volume of the rooms |  | 3
| Task #1 Reading information about cubature of the rooms | 1
| Task #2 Summing cubatures of all rooms for level | 0.5
| Task #3 Summing cubatures of all levels for building | 0.5
| Task #4 Debugging, testing and correction | 1
As a building manager, I can calculate the lighting power per unit area for a building, level, room |  | 3
| Task #1 Reading information about total lighting power and area of a location | 0.5
| Task #2 Writing the formula for a room | 0.5
| Task #3 Writing the formula for a level | 0.5
| Task #4 Writing the formula for the building | 0.5
| Task #5 Debugging, testing and correction | 1
As a building manager, I can calculate the heating energy consumption per unit of volume for a building, level, room |  | 3
| Task #1 Reading information about heating consumption of room | 0.5
| Task #2 Summing heating consumption of rooms on the same level | 0.5
| Task #3 Summing heating consumption of rooms for whole building | 0.5
| Task #4 Calculating heating consumption per needed unit area | 0.5
| Task #5 Debugging, testing and correction | 1
As a building manager, I can receive information about rooms in the building that exceed a certain level of heat consumption / m^3 given as a parameter to find places for improvement in the infrastructure. |  | 3
| Task #1 Reading information about heat consumption of rooms | 0.5
| Task #2 Reusing heat consumption of room function | 1
| Task #3 Searching rooms that exceeds the level | 0.5
| Task #4 Debugging, testing and correction | 1
Sprint 1 Infrastructure and Setup |  | 2026-09-05
| Task #1 Setting up GitHub for the project | 0.5
| Task #2 Creating UML for the project | 6
| Task #3 Setting up CI/CD | 1
| Task #4 Import and customize the base project structure for the Building Info app | 1
| Task #5 Completing documentation for class/interface | 1
Sprint 2 Retrospection and Tests
| Task #1 Adding unit tests (2 classes, 10 methods) | 2
| Task #2 Adding mock test | 1
| Task #3 Creating Sprint 1 Restrospection | 1
| Task #4 Releasing new tag version, with updated wiki | 0.5